## MVP Proposal
Smith Web Development - Project Proposal (MVP)
Client | Find Me Gluten Free
Technology | React • ASP.NET Core • MySQL • Azure/AWS • GitHub
Project Scope
Interactive park map with GPS and filtering
Admin CMS to manage Parks, Maps, Restaurants and Menu Items
Restaurant detail pages
Menu item management
User accounts and reviews
Photo uploads
Community updates pending admin approval
Search and filtering
Responsive mobile-friendly design
Stripe or PayPal integration
Deployment to Azure or AWS
Estimated Cost Breakdown
Phase | Hours | Rate | Total
Discovery & Planning | 10 | 65 | 650
UI/UX Design | 20 | 65 | 1300
Database & Architecture | 18 | 65 | 1170
Frontend Development | 80 | 65 | 5200
Backend/API Development | 70 | 65 | 4550
Interactive Maps | 35 | 65 | 2275
Admin CMS | 55 | 65 | 3575
Authentication | 12 | 65 | 780
Reviews & Community | 35 | 65 | 2275
Payments | 10 | 65 | 650
Deployment & DevOps | 20 | 65 | 1300
QA & Bug Fixes | 30 | 65 | 1950
Project Management | 20 | 65 | 1300
Contingency | 25 | 65 | 1625
Estimated Hours | 440 | Proposal Price | 8500

## Premium Proposal
Premium Project Proposal
Includes everything in MVP plus:
AI chatbot for gluten-free questions
Google Sign-In
Multi-factor authentication
Advanced admin analytics
Automated moderation tools
Push/email notifications
Advanced animations and polished UI
Suggested menu change workflow
Scalable architecture
Phase | Hours | Rate | Total
Discovery & Planning | 10 | 65 | 650
UI/UX Design | 20 | 65 | 1300
Database & Architecture | 18 | 65 | 1170
Frontend Development | 80 | 65 | 5200
Backend/API Development | 70 | 65 | 4550
Interactive Maps | 35 | 65 | 2275
Admin CMS | 55 | 65 | 3575
Authentication | 12 | 65 | 780
Reviews & Community | 35 | 65 | 2275
Payments | 10 | 65 | 650
Deployment & DevOps | 20 | 65 | 1300
QA & Bug Fixes | 30 | 65 | 1950
Project Management | 20 | 65 | 1300
Contingency | 25 | 65 | 1625
AI Chatbot | 35 | 65 | 2275
Google Login | 8 | 65 | 520
MFA | 12 | 65 | 780
Analytics | 25 | 65 | 1625
Notifications | 18 | 65 | 1170
Advanced UX | 30 | 65 | 1950
Automation Tools | 45 | 65 | 2925
Estimated Hours | 613 | Proposal Price | 18000